TIMEline for performance standards

Project manager_____________________________________________  Practice name

| Task description | 16-week suggested time frame | Actual start date | Target completion date | Actual completion date | Person responsible for task completion |
| --- | --- | --- | --- | --- | --- |
| Determine appropriate project manager (management staff or consultant/HR specialist) | Week 1 |  |  |  |  |
| Select project manager | Weeks 3-5 |  |  |  |  |
| Prepare for and hold initial staff meeting and distribute job description questionnaires | Weeks 5-6 |  |  |  |  |
| Complete job questionnaires | Week 7 |  |  |  |  |
| Conduct individual employee meetings to review questionnaire and discuss content | Week 9 |  |  |  |  |
| Observe each employee conducting his or her work to validate/clarify tasks compared to completed job questionnaire | Weeks 9-11 |  |  |  |  |
| Prepare and distribute revised job descriptions | Week 11 |  |  |  |  |
| Prepare initial draft of standards for each position | Week 12 |  |  |  |  |
| Gather data (measure workload volumes) and determine accurate quantifiable measurement for each standard | Weeks 12-14 |  |  |  |  |
| Prepare final draft of standards for each position | Weeks 14-15 |  |  |  |  |
| Hold final staff meeting and implement standards | Week 16 |  |  |  |  |
| Conduct meeting with physicians and manager to review standards and discuss development of standards for physicians | Week 16 |  |  |  |  |

|  | Developed by Judy Capko. Copyright © 2005 American Academy of Family Physicians. Physicians may photocopy or adapt for use in their own practices; all other rights reserved. “Get Better Results With Staff Performance Standards.” Capko J. Family Practice Management. October 2005:40-44; http://www.aafp.org/fpm/20051000/40getb.html. |
| --- | --- |